PROJECT PLAN

AI Face Processing & Integration Project - Phase 1

Face Detection, Cropping, and Core System Setup for AIFX Studio Integration

Prepared for: Zooey / AIFX Studio Phase 1 Review

Prepared on: June 29, 2026

Execution window: 4 working days, starting immediately; Day 1 has 4 hours remaining

Deadline basis: Use July 6, 2026 as the hard deadline stated in email; PDF lists July 27, 2026

Recommended delivery mode: Local Docker prototype first; hosted deployment only if time remains

Executive Summary Phase 1 must deliver a functional, containerized prototype where a logged-in user can upload an image, detect faces with MediaPipe, crop each detected face, store original/cropped assets, preserve exact pixel bounding-box metadata, and review task history. The plan below compresses the PDF requirements into a 4-day execution path with Day 1 focused on setup and risk removal.

# 1. Project Scope and Objectives

The Phase 1 objective is to build the foundation for the later ComfyUI face-swap workflow. The current phase does not need to execute face swapping. It must produce reliable face detection, precise cropping, metadata persistence, storage architecture, authentication, task history, documentation, and a containerized runnable prototype.

Allow users to sign up, log in, and access a protected workspace.

Accept .jpg and .png uploads through a simple frontend.

Use Google AI Edge MediaPipe Vision Tasks FaceDetector for face detection.

Crop all detected faces and handle zero-face or multi-face cases gracefully.

Store exact original-image pixel coordinates: x_min, y_min, width, height.

Persist original image URLs, cropped image URLs, bounding boxes, timestamp, and status.

Provide a task-history dashboard for each user.

Deliver Docker-based local execution and concise setup documentation.

# 2. Assignment Requirement Mapping

| PDF Requirement | Implementation Plan | Acceptance Evidence |
| --- | --- | --- |
| Backend Face Detection | FastAPI endpoint calls isolated MediaPipe service module. | Upload image returns detected faces, crops, and bounding boxes. |
| MediaPipe Vision Tasks | Use Python MediaPipe FaceDetector with model file loaded at startup. | README names model source and local startup behavior. |
| Cropping Logic | Convert relative boxes to original-image pixel boxes; crop with Pillow/OpenCV. | JSON contains x_min, y_min, width, height, image_width, image_height. |
| Database & Authentication | Supabase Auth plus Postgres task_history table. | User can log in and see only own historical runs. |
| Object Storage | Supabase Storage stores originals and cropped faces with UUID filenames. | No production reliance on local disk for persisted assets. |
| User Interface | Streamlit auth guard, workspace upload view, history dashboard. | Three views match PDF UI requirements. |
| Containerization | Dockerfile and docker-compose for backend/frontend. | Evaluator can run locally using README steps. |
| Documentation | .env.example, schema SQL, README, test notes. | Reviewer can initialize and operate the prototype. |

# 3. Recommended Technical Architecture

Recommended stack: FastAPI backend, Streamlit frontend, MediaPipe Vision Tasks for detection, Supabase Auth/Postgres/Storage for persistence, and Docker Compose for local delivery.

| Layer | Chosen Tool | Reason |
| --- | --- | --- |
| Frontend | Streamlit | Fastest route to upload UI, previews, login guard, and history table. |
| Backend | FastAPI / Python 3.12+ | Lightweight API routing and clean separation from face-processing logic. |
| Detection | MediaPipe Vision Tasks FaceDetector | Meets PDF requirement and supports accurate bounding boxes. |
| Image Processing | Pillow or OpenCV | Stable crop operation after MediaPipe box conversion. |
| Auth + Database | Supabase | Managed auth plus Postgres reduces implementation time. |
| Object Storage | Supabase Storage | Same provider as auth/database; UUID filenames and signed/public URLs. |
| Deployment | Docker Compose locally | Satisfies deployment requirement under time pressure; hosted deployment optional. |

# 4. Core Data Model

Supabase Auth should own the user identity. The application database only needs a task history table tied to the authenticated user.

| Field | Type | Purpose |
| --- | --- | --- |
| id | uuid primary key | Unique task identifier. |
| user_id | uuid | References authenticated Supabase user. |
| original_image_url | text | Stored source image URL. |
| cropped_image_urls | jsonb | Array of cropped-face image URLs. |
| bounding_boxes | jsonb | Array of face boxes with pixel coordinates and confidence. |
| status | text | pending / completed / failed. |
| error_message | text nullable | Failure details for debugging and reviewer clarity. |
| created_at / updated_at | timestamp | Task audit trail. |

Bounding-box contract for Phase 2 readiness Every detected face must preserve coordinates relative to the original full-resolution image, not the displayed preview. Required fields: face_index, x_min, y_min, width, height, confidence, image_width, and image_height.

# 5. API and UI Workflow

## 5.1 Backend API

GET /health: service health check.

POST /detect-faces: accepts an image, authenticates user, stores original, detects/crops faces, stores crops, writes task_history.

GET /tasks: returns the authenticated user's task history.

GET /tasks/{task_id}: returns one task detail for review/debugging.

## 5.2 Frontend Views

Authentication Guard: signup/login screen, blocks workspace until authenticated.

Workspace: image upload, original preview, cropped-face preview, coordinates panel.

Task History Dashboard: table of previous runs with status, timestamps, URLs, and bounding-box summary.

# 6. Four-Day Delivery Timeline

| Day | Primary Goal | Detailed Work | Definition of Done |
| --- | --- | --- | --- |
| Day 1 - Jun 29, 4 hours left | Project setup and risk removal | Repo structure, dependency files, FastAPI/Streamlit skeletons, Supabase schema draft, .env.example, MediaPipe single-image smoke test. | Backend and frontend start locally; /health works; README skeleton exists; MediaPipe loading path is known. |
| Day 2 - Jun 30 | Detection and cropping core | Implement MediaPipe service, coordinate conversion, multi-face crop output, zero-face handling, simple local test images. | API returns crops and exact pixel metadata for zero/one/multiple-face cases. |
| Day 3 - Jul 1 | Auth, storage, and history | Supabase Auth, Storage upload, task_history writes, user-scoped history endpoint, frontend result display. | Logged-in user can upload, receive stored original/crop URLs, and view history. |
| Day 4 - Jul 2 | Containerization and handoff | Dockerfile, docker-compose, README, schema SQL, final QA, edge-case testing, screenshots or notes. | Reviewer can run the prototype locally and verify all PDF Phase 1 requirements. |
| Jul 3-Jul 6 buffer | Submission hardening | Bug fixes, optional hosted deployment, final README polish, code review cleanup. | Ready for July 6 email deadline even though PDF states July 27. |

# 7. Immediate First-Day Execution Plan

| Timebox | Action | Output |
| --- | --- | --- |
| 0:00-0:30 | Confirm repo structure and create dependency/env files. | requirements/pyproject, .env.example, folders. |
| 0:30-1:15 | Create FastAPI skeleton and /health endpoint. | Backend starts locally. |
| 1:15-2:00 | Create Streamlit skeleton with login/workspace/history placeholders. | Frontend starts locally. |
| 2:00-3:15 | Run MediaPipe FaceDetector smoke test on one local image. | Known model path and detection response shape. |
| 3:15-4:00 | Draft Supabase schema SQL and README setup steps. | Database/storage plan ready before Day 2. |

# 8. Implementation Flow

Initialize environment and repository: create backend, frontend, core_ai, database, and docs structure.

Build isolated face detector module first: no database or UI dependency inside detection logic.

Expose the detector through FastAPI after the local detector works.

Add storage and database persistence only after crop output is correct.

Connect Streamlit UI to backend and Supabase Auth.

Add history dashboard and user scoping.

Containerize and document exact local startup steps.

Run final QA against assignment checklist before submission.

# 9. Risk Register

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Email and PDF deadlines differ | Possible late delivery if PDF date is trusted. | Execute against July 6, 2026 as hard deadline; treat July 27 as document inconsistency. |
| MediaPipe dependency/model issue | Blocks core requirement. | Smoke test on Day 1 before database/UI work expands. |
| Supabase auth integration takes longer than expected | Could delay user-scoped history. | Use Supabase SDK; if needed, temporarily simplify to single-user demo then restore auth. |
| Storage URL permissions misconfigured | Images may not display in reviewer environment. | Use signed URLs or controlled public bucket; document chosen approach in README. |
| Multi-face and zero-face edge cases missed | Evaluation risk. | Add explicit API handling and manual test cases on Day 2. |
| Docker configuration fails late | Deployment/readiness risk. | Create Docker files before final polish and test on Day 4 morning. |

# 10. Final Acceptance Checklist

[ ] User can sign up and log in.

[ ] Only authenticated users can access workspace and task history.

[ ] User can upload .jpg/.png images.

[ ] MediaPipe detects faces through backend service.

[ ] Every detected face is cropped and previewed.

[ ] Zero-face images return a graceful message, not a crash.

[ ] Multiple faces create multiple crop outputs.

[ ] Bounding boxes are stored as original-image pixel coordinates.

[ ] Original and cropped images are saved to object storage with UUID-style filenames.

[ ] Task history stores URLs, bounding boxes, timestamp, status, and user ID.

[ ] Docker/local startup instructions work from README.

[ ] .env.example and database schema SQL are included.

# 11. Deliverables

| Deliverable | Required for Phase 1 | Notes |
| --- | --- | --- |
| Git repository | Yes | Clean structure and commit history. |
| FastAPI backend | Yes | API routing separated from MediaPipe core. |
| Streamlit frontend | Yes | Authentication, workspace, history. |
| MediaPipe detection module | Yes | Reusable for Phase 2 integration. |
| Supabase schema SQL | Yes | task_history plus storage/auth setup notes. |
| Object storage integration | Yes | Original and crop asset persistence. |
| Docker / docker-compose | Yes | Local deployment path. |
| README.md | Yes | Setup, environment variables, database initialization, run commands. |
| Hosted deployment URL | Optional | Only after local Docker prototype is stable. |

Recommended execution principle Do not spend early time polishing the UI. First make the MediaPipe coordinate and crop pipeline trustworthy. The Phase 2 re-merge workflow depends on accurate metadata more than visual polish.